## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Priyanka Dey | 2026-10-16 | Encountered LangChain deprecation warnings during RAG ingestion and a NameError ('query_knowledge_base' / 'Chroma' / 'PERSIST_DIRECTORY' not defined) when querying the vector store in Streamlit. | Sprint 1 | Priyanka Dey | Standards | Migrated to standalone packages (langchain-huggingface, langchain-text-splitters), defined global paths and imports in rag_engine.py, added @st.cache_resource for performance, and implemented result deduplication in app.py. | 2026-10-16 | Closed | All import errors, missing paths, and deprecation warnings have been fully resolved; the RAG knowledge base runs efficiently and renders unique search results seamlessly.
3 | Priyanka Dey | 2026-10-28 | Overlapping regex patterns between security and quality agents resulted in duplicate finding cards appearing on the same line. | Sprint 2 | Priyanka Dey | Logical | Implemented advanced line-grouping logic and severity merging inside workflow.py to unify multi-agent issues cleanly. | 2026-10-25 | Closed | Verified that all multi-agent findings now render uniquely with prioritized high severities per line.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others